Ministry of Agriculture

Tree Crop Extension Project-II (TCEP-II)

Request for Expression of Interest

for

Consulting Services for TCEP-II Outcome Survey

Ref No: LIB/IFAD/TCEP-II/CS-004/25

Issue Date:  November 17, 2025

Instructions to Consultants

Reference Number:

Date: November 17, 2025

- Consulting Services for TCEP-II/RPSFP Outcome Survey

The Government of The Republic of Liberia received financing from the International Fund for Agricultural Development (“the Fund” or “IFAD”) towards the cost of the Tree Crop Extension Project-II (“the client” or “procuring entity”), and intends to apply part of the proceeds for the recruitment of consulting services, for which this REOI is issued.

- The use of any IFAD financing shall be subject to IFAD’s approval, pursuant to the terms and conditions of the financing agreement, as well as IFAD’s rules, policies and procedures. IFAD and its officials, agents and employees shall be held harmless from and against all suits, proceedings, claims, demands, losses and liability of any kind or nature brought by any party in connection with TCEP-II Project.

The client now invites expressions of interest (EOIs) from legally constituted consulting firms (not individual consultants) (“consultants”) to conduct TCEP-II Outcome Survey. More details on these consulting services are provided in the preliminary terms of reference (PTOR) attached as Annex 1.

Before preparing its EOIs, the consultant is advised to review the preliminary terms of reference attached as Annex 1, which describe the assignment and Annex 2 that details the evaluation of the technical qualifications.

The consultant shall not have any actual, potential or reasonably perceived conflict of interest. A consultant with an actual, potential or reasonably perceived conflict of interest shall be disqualified unless otherwise explicitly approved by the Fund. A consultant including their respective personnel and affiliates are considered to have a conflict of interest if they a) have a relationship that provides them with undue or undisclosed information about or influence over the selection process and the execution of the contract, b) participate in more than one EOI under this procurement action, c) have a business or family relationship with a member of the client’s board of directors or its personnel, the Fund or its personnel, or any other individual that was, has been or might reasonably be directly or indirectly involved in any part of (i) the preparation of this expression of interest, (ii) the selection process for this procurement, or (iii) execution of the contract. The consultant has an ongoing obligation to disclose any situation of actual, potential or reasonably perceived conflict of interest during preparation of the EOI, the selection process or the contract execution. Failure to properly disclose any of said situations may lead to appropriate actions, including the disqualification of the consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

All consultants are required to comply with the Revised IFAD Policy on Preventing Fraud and Corruption in its Activities and Operations (hereinafter, “IFAD’s Anticorruption Policy”) in competing for, or in executing, the contract.

  - If determined that a consultant or any of its personnel or agents, or its sub-consultants, sub-contractors, service providers, suppliers, sub-suppliers and/or any of their personnel or agents, has, directly or indirectly, engaged in any of the prohibited practices defined in IFAD’s Anticorruption Policy or integrity violations such as sexual harassment, exploitation and abuse as established in IFAD’s Policy to Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse in competing for, or in executing, the contract, the EOI may be rejected or the contract may be terminated by the client.

  - In accordance with IFAD’s Anticorruption Policy, the Fund has the right to sanction firms and individuals, including by declaring them ineligible, either indefinitely or for a stated period of time, to participate in any IFAD-financed and/or IFAD-managed activity or operation. The Fund also has the right to recognize debarments issued by other international financial institutions in accordance with its Anticorruption Policy.

  - Consultants and any of their personnel and agents, and their sub-consultants, sub-contractors, service providers, suppliers, sub-suppliers and any of their personnel and agents are required to fully cooperate with any investigation conducted by the Fund, including by making personnel available for interviews and by providing full access to any and all accounts, premises, documents and records (including electronic records) relating to this selection process or the execution of the contract and to have such accounts, premises, records and documents audited and/or inspected by auditors and/or investigators appointed by the Fund.

  - Consultants have the ongoing obligation to disclose in their EOI and later in writing as may become relevant: (i) any administrative sanctions, criminal convictions or temporary suspensions of themselves or any of their key personnel or agents for fraud and corruption, and (ii) any commissions or fees paid or to be paid to agents or other parties in connection with this selection process or the execution of the contract. As a minimum, consultants must disclose the name and contact details of the agent or other party and the reason, amount and currency of the commission or fee paid or to be paid. Failure to comply with these disclosure obligations may lead to rejection of the EOI or termination of the contract.

  - Consultants are required to keep all records and documents, including electronic records, relating to this selection process available for a minimum of three (3) years after notification of completion of the process or, in case the consultant is awarded the contract, execution of the contract.

The Fund requires that all beneficiaries of IFAD funding or funds administered by IFAD, including the client, any consultants, implementing partners, service providers and suppliers, observe the highest standards of integrity during the procurement and execution of such contracts, and commit to combat money laundering and terrorism financing consistent with IFAD’s Anti-Money Laundering and Countering the Financing of Terrorism Policy.

Procedure: the selection process will be conducted using Least Cost Selection (LCS) as laid out in the IFAD Procurement Handbook that can be accessed via the IFAD website at www.ifad.org/project-procurement. Only the highest-ranked firm will be invited to submit a combined technical and financial proposal. If such proposal is responsive and acceptable, the firm will be invited for negotiation. Both technical and financial aspects of the proposal may be negotiated. If negotiations with the selected firm fail, the procuring entity may terminate the negotiations after obtaining IFAD’s no objection (NO) and invite the second-ranked consultant to submit a combined technical and financial proposal.

Consultants may associate with other firms to enhance their qualifications but should indicate clearly whether the association is in the form of a joint venture and/or a sub-consultancy. In the case of a joint venture, all the partners in the joint venture shall be jointly and severally liable for the entire contract, if selected.

Any request for clarification on this EOI including the PTOR should be sent via e-mail to recruit@moa.gov.lr  no later than November 25, 2025. The client will provide responses to all clarification requests by November 28, 2025 before the close of business or not later than 4:00 PM.

Submission Procedure: Please submit your expression of interest using the forms provided for this purpose. Your EOI should comprise one (1) original copy of each EOI form annexed to this document. EOIs shall be submitted to the address below no later than December 8, 2025 not later than 4:00 PM to the address below:

IFAD PIU/PMU/MOA

Ministry of Agriculture Annex, Libsuco Compound

Somalia Drive, Gardnerville, Montserrado County

Telephone: 0775901977

recruit@moa.gov.lr , Cc:  ddoe@moa.gov.lr  evah@moa.gov.lr

Yours sincerely,

---------------------

# Form EOI-1

# EOI Submission Form

- Re: Consulting Services To Conduct TCEP-II Outcome Survey

Ref: LIB/IFAD/TCEP-II/CS-004/25

We, the undersigned, declare that:

- We are expressing our interest in providing the consulting services for the above-mentioned assignment and have no reservations to the REOI, the instructions to the consultants and any addenda thereto.

- Our expression of interest is open for acceptance for a period of ninety (90) days.

- Our firm, its associates, including any subcontractors or suppliers for any part of the contract, have not been declared ineligible by the Fund and have not been subject to sanctions or debarments under the laws or official regulations of the client’s country or not been subject to a debarment recognized under the Agreement for Mutual Enforcement of Debarment Decisions (the "Cross-Debarment Agreement"), beyond those declared in paragraph 9 of this EOI submission form.

- We acknowledge and accept the IFAD Revised Policy on Preventing Fraud and Corruption in its Activities and Operations. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any prohibited practices as provided in ITC Clause 6. Further, we acknowledge and understand our obligation to report to anticorruption@ifad.org any allegation of prohibited practice that comes to our attention during the selection process or the contract execution.

- No attempt has been made or will be made by us to induce any other consultant to submit or not to submit an EOI for the purpose of restricting competition.

- We acknowledge and accept the IFAD Policy on Preventing and Responding to Sexual Harassment, Sexual Exploitation and Abuse. We certify that neither our firm nor any person acting for us or on our behalf has engaged in any sexual harassment, sexual exploitation or abuse. Further, we acknowledge and understand our obligation to report to ethicsoffice@ifad.org any allegation of sexual harassment, sexual exploitation and abuse that comes to our attention during the selection process or the contract execution.

- The following commissions, gratuities, or fees have been paid or are to be paid with respect to the selection process: [Insert complete name of each recipient, its full address, the reason for which each commission or gratuity was paid and the amount and currency of each such commission or gratuity.]

| Name of Recipient | Address | Reason | Amount | Currency |
| --- | --- | --- | --- | --- |

(If none has been paid or is to be paid, indicate “none.”)

- We declare that neither our consulting firm nor any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners have any actual, potential or perceived conflict of interest as defined in ITC Clause 5 regarding this selection process or the execution of the contract. [insert if needed: “other than the following:” and provide a detailed account of the actual, potential or perceived conflict]. We understand that we have an ongoing disclosure obligation on such actual, potential or perceived conflicts of interest and shall promptly inform the client and the Fund, should any such actual, potential or perceived conflicts of interest arise at any stage of the procurement process or contract execution.

- The following criminal convictions, administrative sanctions (including debarments) and/or temporary suspensions have been imposed on our consulting firm and/or any of its directors, partners, proprietors, key personnel, agents, sub-consultants, sub-contractors, consortium and joint venture partners:

| Nature of the measure (i.e., criminal conviction, administrative sanction or temporary suspension) | Imposed by | Name of party convicted, sanctioned or suspended (and relationship to the consultant) | Grounds for the measure (i.e., fraud in procurement or corruption in contract execution) | Date and time (duration) of measure |
| --- | --- | --- | --- | --- |

If no criminal convictions, administrative sanctions or temporary suspensions have been imposed, indicate “none”.

- We acknowledge and understand that we shall promptly inform the client about any material change regarding the information provided in this EOI submission form.

- We further understand that the failure to properly disclose any of information in connection with this EOI submission form may lead to appropriate actions, including our disqualification as consultant, the termination of the contract and any other as appropriate under the IFAD Policy on Preventing Fraud and Corruption in its Projects and Operations.

- We understand that you are not bound to accept any EOI that you may receive.

| [Authorized signatory] |  |
| --- | --- |
| [Name and title of signatory] |  |
| [Name and address of firm] |  |

## Form EOI-2 
Organization of the Consultant

Re: Consulting Services for [insert assignment]

Ref: [insert]

[Provide a brief description of the background and organization of your firm/entity and of each associated firm for this assignment. Include the organization chart of your firm/entity. The EOI must demonstrate that the consultant has the organizational capability and to carry out the assignment. The qualifications document shall further demonstrate that the consultant has the capacity to field and provide experienced replacement personnel on short notice. Key staff CVs are not required at the shortlisting stage.]

| Name of the firm |  |
| --- | --- |
| Date of establishment |  |
| Country of registration |  |
| Full address of the firm |  |
| Focal point: name, position, contact information (telephone, email): | Name: |
|  | Tel: |
|  | Email: |
| Number of branches in the country |  |
| Country(ies) of operations with number of branches in each country |  |
| Number of full-time employees |  |
| Number of part-time employees |  |
| Field(s)of expertise of the firm |  |
| Number of professional staff with experience related directly to the assignment |  |
| Subsidiary and associated companies (wherever applicable): (details in the following format to be provided for all associates) – - Name of the company - Nature of business - Address of the company - Website of the company - Brief description of company (maximum of 120 words) |  |
| Any other information that the consultant would like to add: |  |

Maximum 10 pages

## Form EOI-3

## Experience of the Consultant

Re: Consulting Services for [insert assignment]

Ref: [insert]

[Using the format below, provide information on each relevant assignment for which your firm, and each associate for this assignment, was legally contracted either individually as a corporate entity or as one of the major companies within an association, for carrying out consulting services similar to the ones requested under the preliminary terms of reference included in this EOI. The EOI must demonstrate that the consultant has a proven track record of successful experience in executing projects similar in substance, complexity, value, duration, and volume of services sought in this procurement.

Maximum 20 pages]

| Assignment name: | Approx. value of the contract (in current US$): |
| --- | --- |
| Country: Location within country: | Duration of assignment (months): |
| Name of client: | Total No. of staff-months of the assignment: |
| Address, and contact details (including email address(es)): | Approx. value of the services provided by your firm under the contract (in current US$): |
| Start date (month/year): Completion date (month/year): | No. of professional staff-months provided by associated consultants: |
| Name of associated consultants, if any: | Name of proposed senior professional staff of your firm involved and functions performed (indicate most significant profiles such as project director/coordinator, team leader): |
| Narrative description of project: |  |
| Description of actual services provided by your staff within the assignment: |  |

Name of Firm: _________________________________

ANNEX 1

PRELIMINARY TERMS OF REFERENCE

Consulting Services for TCEP-II Outcome Survey

1.	Client

The client for this assignment is the TCEP-II Project, IFAD PIU

2.	Background on Project

- The Ministry of Agriculture is implementing the Tree Crop Extension Project II (TCEP-II) with funding from the International Fund for Agricultural Development (IFAD). The project is designed to reach about 15,000 households (HHs) of which 10,000 HHs will be from the cocoa smallholder farmers; the other 5,000 farming HHs will benefit from roads, input supplies, market linkages and spillover effects along the value chain. Considering an average household size of 4.28, this adds up to 64,200 household members.  The Tree Crops Extension Project II (TCEP II) is also designed to build on the achievements and capitalize on lessons learned from the IFAD co-financed Smallholder Tree Crop Revitalization Support Project (STCRSP) implemented in Lofa County over the last five years and which came to an end in September 2017. The project implementation started in 2020 and will be completed by 2027

- The goal of TCEP-II will be to “increase income and improve the livelihoods of poor rural households farming cocoa on a smallholder basis in Lofa County”. `The Project Development Objective (PDO) of TCEP-II is to improve incomes and climate resilience of smallholder cocoa producers in Lofa County. The objective of the project is to improve incomes and climate change resilience of smallholder cocoa producers, particularly women-headed households, youths and Farmers Based Organizations (FBOs). The project objective will be accomplished through the following four components:

- Component 1: Revitalization of Cocoa Plantations. The expected outcome of Component 1 will be “increased quantity and quality of cocoa sold by smallholders”. Component 1 will involve five Subcomponents as follows: a) Subcomponent 1.1 - Basic Rehabilitation and New Cocoa Plantations; b) Subcomponent 1.2 - Improving Post-Harvest Handling and Quality; c) Subcomponent 1.3 – Germplasm Garden Support; d) Subcomponent 1.4 - Alternative Livelihood Agricultural Activities (crop diversification through intercropping on existing plantations for food and nutrition security, shade management needs and to help generate and protect income flow on new plantations before newly planted cocoa start to produce); and e) Subcomponent 1.5 – Transformation of Cocoa Waste as an Alternative Source of Incomes.

Component 2: Rehabilitation and Maintenance of Roads. The expected outcome of Component 2 will be “improved and climate-proofed access to markets”. It contains two subcomponents. a) Subcomponent 2.1 -Road Construction, Rehabilitation and Climate Proofing. Approximately 110 km of Feeder (or secondary) roads and 270 km of Farm Tracks roads will be rehabilitated and climate-proofed; and b) Subcomponent 2.2 - Maintenance of Roads.

- Component 3: Service provision for value chain development. The outcome of Component 3 will be: “improved value chain organization and performance”. This will be achieved through a set of concurrent activities using the following subcomponents: a) Subcomponent 3.1 - Support to Farmer Organizations (including the establishment of a Platform or Platforms, for value chain players) to discuss sector and business arrangements); b) Subcomponent 3.2 -Improved market linkages with the construction of humidity-controlled warehouses to store cocoa beans during the wet season when roads are not practicable  and c) Subcomponent 3.3 - Support to Extension Service Development and Outreach; d) Subcomponent 3.4 - Dry storage; and e) Subcomponent 3.5 - REDD+ strategy implementation support.

Component 4: Project Coordination, Management and M&E and Policy. Under the country Programme approach, TCEP-II will adopt a similar approach to that of TCEP. This will ensure effective and efficient strategic and operational planning, implementation, monitoring and evaluation, as well as knowledge management while considering environmental and climate change resilience. In addition, Component 4 will work on improved policy engagement and will drive forward gender and social inclusion activities and the dialogue related to the establishment of a functional Road Maintenance Fund.

The project is being implemented in seven (7) districts in Lofa County for a period of six (6) years. The project will adopt a value chain approach to link cocoa farmers, organized at grassroots level in traditional community-based labor groups and FFS, to markets and services through cooperatives and Private Sector Partners (PSPs).

3.	Background of the assignment

As per the IFAD Core Outcome Indicator (COIs) guidelines, it is mandatory for IFAD-funded projects to conduct baseline, mid-term, and completion surveys based on the COI methodology. The COIs guidelines became effective in 2019 replacing the Results and Impact Management System (RIMS), which is based on Annual Outcome Survey (AOS) methodology. IFAD COIs survey results are used to:

(i) Update project log-frame and assess whether the project is on track or not to achieve their outcome targets (including forecasts);

(ii) conduct statistical analysis (possibly combing with other data sources) to better understand the drivers of performance;

(iii) the COI, therefore, is not only a measurement tool but rather a trigger to evaluative reasoning in frontline managers for data-driven and adaptive decision-making to accelerate delivery. The TCEP-II Outcome Survey data will be collected on households benefiting from the project living in the targeted project communities.

4.	Overall objectives

The main purpose of the TCEP II Outcome Survey is to assess the project’s progress and performance by comparing the outcome indicators, their targets and baseline values. To this end, the survey will systematically collect and analyze data to evaluate not only the overall performance of the project but also the effectiveness of its implementation approach in achieving the stated objectives. This survey will enable the PIU identify any risks linked to the achievement of results and sustainability of the project, make evidence-based recommendations, and implement those adjustments to ensure that the project remains aligned with its intended outcomes.

5.	Scope of work

The tasks of the outcome survey under this assignment will specifically cover household information, farmers’ access to production resources, knowledge gained, access to market due to farm-to-market roads construction, job creation, farmers’ cultivation and farmers’ organizations related information. The scope of the services required under this assignment will include the collection of data for the outcome survey (at the appropriate level of analysis, namely, the individual, household and community level). The outcomes measured will be consistent with the with the IFAD COI which support project’s theory of change,  MOA development's objectives and IFAD's corporate mandate.

It is estimated that the sample size will be approximately 1500 households, including 750 treated and 750 control households drawn from 40 communities in TCEP II project intervention areas in Lofa County.

Generally, the required services will include the following:

- Consulting firm will lead the development of the survey methodology with technical inputs from MOA/IFAD technical team. The consulting firm will lead the development of on the sample size, the sample frame, and designing the household questionnaire in line withIFAD’s sampling guidelines.  Specifically, the consulting firm is expected todevelop tailored, context-specific questions that reflect the country context and the project logic , and to provide context-specific inputs for designing survey tools that effectively capture IFAD’s COI.

- The consulting firm will also develop questions for the project specific resilience scorecard which will be created  using the Resilience Design and Monitoring Tool (RDMT) with technical guidance from IFAD  experts. The resilience scorecard aims  to: i) provide data to support the targeting of the project’s resilience building investments; and ii) monitor and evaluate the impact of the project interventions on enhancing beneficiaries’ households resilience capacities (see Annex E). The resilience scorecard questions will be incorporated in the COI questionnaires and enabling conditions will be programmed (using the survey tool described in 4.1) to prevent potential  duplication of questions between the two tools.

- Based on the sampling frame, prepare a list of primary and secondary sampling units (such as households, producers’ organization, community groups, etc.)) for the identified project areas. Specifically, the consulting firm must prepare a household and village enumeration plan in accordancewith the developed survey methodology.

- Develop interview manuals and instructions/guidance notes for field staff (supervisors and enumerators). The interview manual should include a section on unit conversion factors, including but not limited to conversion factors for local units for weights, volumes, areas, time, length, and other relevant measures ;

- Develop an appropriate data management system with adequate statistical analysis capabilities and quality control measures. The data management system should be finalized before the data collection team moves to the field;

- Organize and deliver  training for  supervisors and enumerators on the survey methodology and  questionnaire. Conduct  pre-testing of the questionnaire in project areas that are not selected for sampling;

- Organize and conduct the field activities including all logistic arrangements;

- Administer the household and community level surveys, using questionnaires translated into local languages where necessary, including recording appropriate geo-coordinates for the surveyed households and communities. The consulting firm is also required to map some of the beneficiaries’ farms during the data collection. The quantitative survey must be implemented using a Computer Adaptive Personal Interviewing (CAPI) technique, which should be administered using tablets;

- Deliver datasets on a regular basis to the MOA/IFAD PIU according to the agreed quality standards and in the specific  format. In accordance with  the Survey Solutions or Kobo Collect structure, all responsible  technical staff- including the consulting firm, MOA, and  IFAD PIU- will have ready access to the real time data collected from the field as soon it is  uploaded to the system by the enumerators;

- At the end of the survey period (s), deliver cleaned datasets in Excel or another user friendly format, accompanied by a detailed variable library;

- Prepare and submit an Inception Report within two weeks after the signing of agreement/contract. The report should include a detailed study design including sampling and draft questionnaire (s), work plan, and outline of the outcome report format, based on information provided and discussions with the MOA/IFAD PIU;

- Prepare and submit the final Outcome Survey Report, covering the data collection strategy, sampling distribution, statistical analysis and summary statistics of relevant indicators and key findings to support the project into improving its targeting of investments for enhanced results. The report should also include an analysis of the resilience scorecard data, to providing guidance to the MOA/IFAD PIU oninterventions that are most likely to enhance household resilience capacities. The firm together with the MOA/IFAD PIU, will use the results to update the project log-frame.

- Methodology

The TCEP-II Outcome Survey will focus on quantitative method to obtain required information to assess project progress in line with implementation achievements. The survey will rely on a structured field-based data collection methodology to generate reliable and comparable data across project sites.

It is estimated that the sample size will consist of approximately 1500, comparing  750 control and 750 treated households drawn from 40 communities in the TCEP II intervention areas.

The survey will collect  information aligned with the  results chain of project's theory of change, as reflected in the project log-frame, to effectively  capture outcome-level progress. Data will be collected  using the CAPI-compatible software administered on tablets to enhance accuracy, consistency, and efficiency during field work:

CAPI Administration and Digital Data Collection

- The use of CAPI-compatible software: The consulting firm is required to conduct the survey using CAPI-compatible software,specifically, Survey Solutions, or where appropriate, Kobo Collect, both of which are data collection tools widely recognized and used for surveys and impact evaluations. MOA/IFAD and PIU will provide technical support to the consulting firm in designing the questionnaire in Survey Solutions or Kobo Collect where required;

- Geo-referencing and Location Data: The quantitative surveys conducted at the household and at the community levels must be administered using tablet devices capable of accurately capturing geo-referenced coordinates of household dwelling and  community center. If the tablets lack sufficient GPS functionality, it is the consulting firm’s responsibility to ensure proper GPS devices to ensure accurate spatial data collection;

- Provision and Management of Equipment: The firm will be  responsible for arranging tablet devices that are fully compatible with the latest version of the Survey Solutions or Kobo Collect software. All  devices procured under this assignment will remain the sole property of  IFAD PIU, and must be returned in good condition at the end of the assignment.

The recommended minimum specifications for the tablets is provided below:

Survey Solutions software works with Android tablets with the following specifications:

Version of Android: Android 10 +

RAM Minimum 4 GB, MicroSD, GB

Memory:64GB  
Memory card slot

Battery: 5000mAH +

Processor clock: 2.0 GHz +, with 4 corces

Sim card Slots

WiFi 3G/4G connectivity

Screen size: 8 inches +

Please note that better technical characteristics will improve responsiveness of the program

- Enumerator Training, Pre-Testing and Pilot

The consulting firm is responsible for arranging the pre-testing, the enumerator training as well the pilot phase of the survey tools. The pre-testing exercise aims to :

- Verifying the accuracy of translation;

- Identify questions that may be  difficult for respondents to understand for respondents or may introduce  bias; and

- Identify areas where improvements can be made in the overall questionnaire design, structure, and flow.

The pre-testing team should include all the supervisors and selected local experts (i.e. agronomist or agricultural specialists).

During the pre-testing, the MOA and PIU team will collaborate closely with the consulting firm to refine and finalize the survey tools prior to the enumerator training and the pilot phase. The objective is to ensure that the instruments are well-tailored to Liberia’s  agricultural and socio-cultural context.

The pre-testing should be conducted over  3 days in the fieldwith respondents from communities that are similar to,  but are not part of, the final sample area. Each supervisor must conduct at least two complete household interviews during the exercise.

Once the pre-testing is completed and the survey tools are finalized and translated, the consulting firm will be  responsible for organizing the enumerator training and pilot,  including ensuring that the training venue,  accommodation, and equipment (i.e., tablets, chargers, GPS devices).

During the pilot phase,  each enumerator is required to  complete at least three full interviews, with the third uploaded  to the server to test the data flow and quality control process. It is expected that each pilot interview  will take approximately twice as long as the standard interviewduring the live data collection.

The enumerator training and the pilot should be conducted concurrently. The consulting firm will develop a detailed training schedule based on  the specific needs of the project (i.e. sample size, logistics, type and level of complexity of the intervention, etc.). The training must be  rigorous and comprehensive, covering both the theoretical and practical sessions, including:

- Introduction to the project and survey objectives;

- Review of survey tools and question by question walkthrough;

- CAPI software and device handling;

- Interview techniques and ethical considerations;

- Field practice and mock interviews; and

- Pilot testing and debriefing for tool refinement

Proposed Indicative Training and Pilot Activities Schedule

| Day | Activity |
| --- | --- |
| 1st -3rd days | Pre-testing of questionnaire in Survey Solutions |
| 4th day | Revision and finalization of the questionnaire in Survey Solutions including translation into local language(s) |
| 5th -7th days | Classroom training on Survey Solutions questionnaire |
| 8th day | First pilot of Survey Solutions questionnaire |
| 9th day | Debriefing on first pilot and addressing issues that arose |
| 10th day | (Morning): Second pilot of Survey Solutions questionnaire (Afternoon): Final debriefing and final recommendations for data collection |

It is required that the enumerator training is undertaken in the same location for the entire team, and that all enumerators, supervisors and managers are present. The consulting firm is required to ensure enumerator's capability to collect high quality data within the average amount of time indicated for household survey. To this purpose, the consulting firm must elaborate a plan to verify and test the quality and capability of enumerators and must be prepared to substitute enumerators as needed. This may require higher number of enumerators attending the enumerator training and pilot, after which, the consulting firm will screen out enumerators based on their performance during training and pilot.

- Deliverables of the assignment

The consulting firm will be expected to deliver the following outputs:

| Expected Outputs | Required Completion |
| --- | --- |
| Prepare and submit inception report at the start of the assignment with detailed study design and wok plan based on information provided and discussions with the Project Coordinator or Designated Staff for the study as well the outline of the outcome report format. | Month 1 |
| In collaboration with the MOA/IFAD PIU M&E Team, finalize survey instruments (Questionnaire: producers, POs); and develop interview manuals and instructions for field staff (supervisors and enumerators). The interview manual should include a section on unit conversion factors, including but not limited to conversion factors for local units for weights, volumes, areas, time, length, etc. | Month 1 |
| In collaboration with the MOA/IFAD PIU M&E Team, conduct training for supervisors and enumerators in the use of the data collection tools. | Month 1 |
| In collaboration with MOA/IFAD PIU M&E Team, carry out Pre-testing of questionnaires and make relevant changes based on outcome from the pre-testing exercise. | Month 1 |
| Carry out field data collection in Lofa County + all data cleaning processes. Ensure MOA/IFAD PIU M&E Team have ready access to the data collection platform to monitor data quality | Month 1-2 |
| Carry out data analysis, report writing and submit draft outcome report and raw data set (both hard & softcopies) to MOA/IFAD PIU for review | Month 3 |
| Conduct workshop for presentation of outcome survey findings | Month 3 |
| Submit final report outlining key finding as per the outcome and impact indicators of the TCEP-II project objectives developed and submitted. | Month 3 |

- Timing of the Assignment

The duration of the Outcome survey for TCEP-II / RPSFP is three months from the date of signing the contract. The tentative timeframe of the survey is presented below:

| #### S/N | #### Activities | #### Month 1 |  |  |  | #### Month 2 |  |  |  | #### Month 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | #### 1 | #### 2 | #### 3 | #### 4 | #### 1 | #### 2 | #### 3 | #### 4 | #### 1 | #### 2 | #### 3 | #### 4 |
| #### 1 | #### Inception - Finalize Survey Tools |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 2 | #### Training to Enumerators |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 3 | #### Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 5 | #### Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 6 | #### Draft Report Submission |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 7 | #### Workshop for presentation of survey findings |  |  |  |  |  |  |  |  |  |  |  |  |
| #### 8 | #### Final report submission |  |  |  |  |  |  |  |  |  |  |  |  |

- Qualification and Experience of consulting firm

The consulting firm shall possess the following qualifications:

A. General Experience:

- Must be a legally registered organization whose core activities are in research, and must have existed for at least 5 years.

- Must have experience in conducting baseline, mid-term, and endline evaluation or other similar study in the agriculture sector or other related fields in Liberia or within the sub-region.

B. Specific Experience:

- Must have proven track records of successfully completing at least 10 projects in the similar field. This should be accompanied by at least reference letters and at least three certificates of successful and satisfactory completion of task in a given time. Submit evidence of at least 10 most recent projects completed.

- Proven skills in conducting computerized quantitative analysis, poverty assessment (pro-poor), gender and youth sensitive evaluations, stakeholders profiling and engagement, etc.

- A Clear and well-structured research methodology to successfully carry out the task, including data management plan;

- Strong knowledge in at least two of the following software programs: CAPI, Kobo Collect, Survey Solutions, SPSS, Stata, Power BI.

- Proven records of effectively and efficiently completing similar tasks with high quality reports and performance.

C. Staff/Personnel qualification and relevant work experience :

- Have key staff with at least master’s degrees in any of the following professions: Agriculture, Research/Statistics, Agricultural economics, Agri-business, Applied economics, Rural/Regional development, International development, and other social sciences, M&E, Data management;

- Key staff must have relevant work experience in line with the assignment, such as previous experience in baseline/mid-term/endline evaluation, research, etc.

  - Qualifications and experience firm’s key proposed staff.

Consultant firms are encouraged to develop their own methodology, staffing plan, level of effort, and work approach to accomplish the TORs.  The firms shall have key staff with relevant education and proven experiencein research, particularly in  baseline, mid-term, and endline surveys. The team proposed for the assignment shall include the following staff:

Key expert 1: Survey/Project Manager/Research Specialist

Qualifications and skills

Minimum Master's degree in Agriculture Economic/Applied Economic, Research, Development Study or related fields of study.

General professional experience

The person should have 8-10 years of experience in Research works, preferably Agriculture development projects.

Specific professional experience

At least   8 years’ experience in leadership and management positions in area of research coordination, planning, etc. Must have work on baseline, mid-term and/or end line surveys.

Key expert 2: Data Manager/Data Analyst

Qualifications and skills

Minimum Master's degree in Data management/Data Science, ICT, or related field of study.

General professional experience

The person should have 8 years of experience in data management, data analysis, or related fields

Specific professional experience

At least 5 years of experience in data management, data analysis and interpretation. Must have knowledge in contemporary data management tools. Must have worked on baseline, outcome and end-line survey.

Key expert 3: Agricultural Specialist/Agricultural Economist

Qualifications and skills

At least master’s degree in Agriculture, Agricultural Economic, or related field of study.

General professional experience

At least 10 years of professional experience in Agriculture development project, agriculture search, baseline, outcome, and end-line surveys

Specific professional experience

At least 8 years of experience in baseline, outcome, and end-line surveys. Knowledgeable about the Liberia agriculture sector.

Key expert 4: M&E Specialist/Knowledge Management and Communication

Qualifications and skills

At least Bachelor’s degree or advance diploma in Monitoring and Evaluation, Project Management, or related field of study.

General professional experience

At least 8 years of professional experience in Monitoring and Evaluation/Knowledge management and communication, and project management.

Specific professional experience

At least 5 years of experience in conducting baseline, outcome and end line survey.

Data Collectors:

Have key data collectors with experience in field and household data collection using mobile based data collection tools, including Kobo Collect, Survey Solution.

- Procurement Method

Due to the specific requirements  of the project’s Outcome Survey (i.e., the use of IFAD’s Core Outcome Indicators  - COI Methodology), the PIU requests that REOI be opened to international, regional, and national firms with proven expertise in IFAD’s COI Methodology through the Least Cost Selection Method (LCS).

Note: The assignment may require a degree of flexibility and modification as  new information becomes available,  including additional tasks to be agreed upon with the Project Coordinator and Head M&E Officer. Should additional working days be required, these be agreed with the Project Coordinator in advance, following discussion of workload management but at no cost.

- Applications:

Please send a soft copy of your expression of interest by on or before December 8, 2025, by 4.00pm to:

ifadrecruit@moa.gov.lr , Cc:   ddoe@moa.gov.lr , evah@moa.gov.lr

IFAD PIU/PMU/MOA

Ministry of Agriculture Annex, Libsuco Compound

Somalia Drive, Gardnerville, Montserrado County

Telephone: 0775901977

The subject line should read: EOI for Consulting Services for TCEP-II  Outcome Survey

Only pre-selected consulting firms will be contacted.

B. RDMT Resilience Scorecard Methodology

Resilience Design and Monitoring Tool (RDMT) Resilience Scorecard Methodology

The Resilience Design and Monitoring Tool (RDMT) consists of a matrix that builds the project’s ToC, placing resilience at the core. The RDMT has 7 steps - corresponding to the columns in the resilience scorecard matrix (figure A). It begins by defining shocks and stresses, grouped into five overall risk types that affect  rural communities targeted by IFAD-supported projects (column A).

Steps 1 to 4 (column B-E) guide design teams in integrating resilience considerations into the project’s ToC. Draft questions for the household resilience scorecard – used to monitor progress in building expected resilience capacities- are developed during project design (step 5/column F and step 6/column H) and later refined in collaboration with the PIU and the firm contracted to conduct the project’s baseline survey at the start- up.

Once the field data are collected, resilience scores are calculated in step 7. The survey and calculation of resilience scores are repeated during the project’s midterm survey and completion survey, and  may also be applied in outcome surveys.

Figure A: Resilience Design and Scorecard Matrix

| A. Risk Type | B. Specific risks (Step 1) | C. Vulnerability (Step 2) | D. Project interventions (Step 3) | E. Expected results (Step 4) | F. Adoption monitoring questions (Step 5) | G. Adoption score | H. Resilience capacity monitoring question (Step 6) | I. Results score | J. Resilience Index (Adoption score x Result Score) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Climate change, degraded natural resources |  |  |  |  |  |  |  |  |  |

The fully developed matrix for the TCEP-II will be provided in an Excel File, including all formulas, to the service provider selected for this consultancy.

The steps 1 to 4 have been done as part of the project design for building resilience capacities. The most important columns for developing the questionnaire to be used in the field for the outcome survey are column F (step 5) and column H (step 6) for which proposed questions have also been prepared (see Annex E below). The steps explaining all the columns and the reasoning behind the questions are as follows:

1) STEP 1: Identify key risks from shocks and stressors: what are the shocks and stresses that have historically caused or are causing losses and damage to or preventing the development of livelihood activities of the different project target groups in the project area? What have been historical and what are the current impacts? Are some shocks and stressors more important than others in terms of strength, frequency and depth of impact and do some shocks and stresses impact some target groups more than others?  Data are grouped according to five main categories of risk types: i) climate and degraded ecosystems; ii) lack of governance and insecure access and tenure to land and other natural resources; iii) social and cultural exclusion drivers limiting women, youth, indigenous peoples and other vulnerable groups' participation in economic and livelihood development activities; iv) health risks linked to poor nutrition and exposure to diseases outbreaks; and v) insecure access to markets, market fluctuations and other economic factors. TCEP-II will only use the category of risk i) climate and degraded ecosystems. COLUMN A and B.

2) STEP 2: Identify key vulnerabilities and impacts (development problem): What makes the households in the different target groups particularly prone to the impacts (losses and damages or limitations to the development of current and new livelihood activities) caused by the identified risks from shocks and stressors? What makes them particularly exposed and sensitive to these risks? What are current coping strategies and what do the target groups think could help them to cope better? What are the households lacking to be able to plan and anticipate (prevent impacts) from shocks and stressors, absorb (recover and withstand) and adapt (build-back better and make changes in livelihood activities) to a shock or stress? What is lacking now to be able to withstand future shocks and stresses? COLUMN C.

3) STEP 3: Identify project interventions: Project interventions are designed to address the vulnerability identified in STEP 2. Interventions will be directed to enhancing the capacity of households to anticipate, absorb and/or adapt to shocks and stresses identified in STEP 1, and therefore reducing the vulnerabilities identified in STEP 2. COLUMN D.

4) STEP 4: Identify the expected result: Every intervention is associated with expected results in terms of: i) adoption - what the households and their communities should have adopted, have access to or changed in behavior; and ii) results - e.g. access to sufficient water for production needs, reduction in losses and stability or gains in production, food security and/or income despite the identified shocks and stressors due to the enhanced resilience capacity. Clarifying expected results both in terms of adoption and results, will underpin the next two steps (STEP 5 and STEP 6) in both the formulation of the adoption and the results question as well as in the definition of the possible answers assigned different scores (see STEP 5 and 6 below). COLUMN E.

Figure B: Example of step 1-4 for one resilience building intervention

| RISK TYPE | SPECIFIC RISK (step 1) | RELATED VULNERABILITY (step 2) | PROJECT INTERVENTIONS (step 3) | EXPECTED RESULT (step 4) |
| --- | --- | --- | --- | --- |
| Climate change, degraded natural resources and ecosystem services risks | The overall decline of average climatic suitability of traditionally produced cocoa varieties. Risk of years with above-average temperatures and below-average dry season rainfall implies an increased risk of crop failure. | Planting material is not sufficient and not adopted to specific and changing climatic conditions. | Establishment and Operation of a Germplasm Station and Village Nurseries for cocoa planting and grafting material that is climate resilient and specific to the hotter conditions of Nimba County. | Improved yields and higher quality of cocoa |

5) STEP 5:  Measure if the project intervention has been adopted/has created the expected change in behavior/status: In this step, monitoring questions are formulated to allow assessing if the project intervention has been adopted. The answers to the questions are scored with (0) no adoption, (1) partially adoption, and (2) full adoption. In some cases, it might require two linked questions to assess to what extent, the project intervention has been adopted COLUMN F. Assigning scores 0,1, or 2 to the answers will allow the project team, survey company and the participating communities to transform qualitative observations into quantitative variables in the final adoption index for each household and monitor progress in adopting resilience enhancing measures. The (0) score is assigned whenever the answer to all adoption questions are NO meaning no adoption. The (2) score is assigned whenever the answer to most or all questions are YES indicating interventions have been fully adopted. The score (1) is assigned when some but not all questions are answered with YES indicating the project intervention has been only partially adopted. COLUMN G.

6) STEP 6: Measure the households' perception of the results of the adoption of the resilience building interventions in terms of gained resilience capacities: In this step, monitoring questions are formulated to allow assessing if the project intervention is producing the expected results. The (0) score is assigned whenever there is no result on resilience capacities achieved and detected in terms of what was expected  in the intervention’s ToC. The score (1) is assigned when the expected resilience result is partially being achieved and detected. The (2) score is assigned whenever the expected resilience result is fully achieved and detected. The effectiveness of the resilience intervention is defined as the extent to which the adoption of the project intervention produces expected results in terms of enhanced resilience capacity.

The score assigned through this step is used as a weight reflecting the importance of the intervention for the calculation of the combined resilience score (the adoption score multiplied with the results score of an intervention). This also means that if a result is not achieved despite full adoption the combined resilience score will be 0. COLUMN H.

Figure C: Example of step 5 and 6 for one resilience building intervention

| MONITORING QUESTION FOR IF THE INTERVENTION HAS BEEN ADOPTED (Step 5) | ADOPTION SCORE | MONITORING QUESTION OF THE RESULT OF THE DESIRED RESILIENCE CAPACITY (Step 6) | RESULT SCORE |
| --- | --- | --- | --- |
| 2.1 Do you or a member of your household have access to cocoa village nurseries, seed hybrids and services from germplasm stations? |  | 1.2. Is the cocoa planting material you use sufficient resistant to diseases and droughts, allowing you to have increase or stability in quality and quantity in your cocoa harvest also in a particular dry year? in the last season? |  |
| Score: No: 0 Yes: 2 |  | Score: Yes, increase/stability in quality and quantity: 2 points Yes, increase/stability in either quality or quantity: 1 point No: 0 points |  |

7) STEP 7: Data analysis: In this last step the final household adoption index and resilience index is calculated for each household surveyed as well as the average indices for all households surveyed disaggregated by treated and control groups. Various disaggregation and comparison data analysis can subsequently be done e.g. between different sub regions, agro-ecological zones, target groups, gender, and age, etc. Data analysis of the RDMT is based on two indexes (figure D) and can produce valuable information on both investments targeting and resilience monitoring:

ADOPTION INDEX: Based on the adoption scores an adoption index for each household is calculated by dividing the SUM of all the adoption scores achieved by the household (column G) by the maximum adoption score possible if all interventions were fully adopted (i.e. the total number of interventions included in the scorecard multiplied by 2). This number, calculated as a percentage, expresses the extent to which the project interventions have been adopted by the household {Excel formula: =SUM(G:Gn)/(ROWS(G:Gn)*2}.

RESILIENCE INDEX: Based on the adoption scores and the result scores the resilience index for the household is calculated by: 1) multiplying each adoption score (column G) by the corresponding result score (column H) to obtain the resilience score for each intervention (column I); and 2) dividing the SUM of the resilience scores achieved by the household by the maximum resilience score possible if all interventions had been fully adopted and fully achieved the desired resilience results (i.e. the total number of interventions included in the scorecard multiplied by 4). {Excel formula: =SUM(I:In)/(ROWS(I:In)*4)}. The final resilience index for the project can be calculated as the average of all household resilience indices.

Figure D: Calculating the indexes

In the Annex E below, questions and the scoring of the answers have been extracted from the RDMT table developed for the TCEP-II project. The wording of the questions will be fine-tuned during the guidance session to be held with the service provider, staff from the PIU and IFAD experts at the beginning of the consultancy. The final agreed questions are to be included in the baseline household survey questionnaire and the field interviewers must be trained in the methodology behind and the scoring system.

Annex E: Resilience Design and Monitoring Tool (RDMT) Questions

| Question not to be reflected in the score: Which of the following practices do you use in your cocoa production? [ ] Cultural practices including the hand picking of cocoa with black pod disease [ ] Cutting of infested branches [ ] Using standard doses of fungicide [ ] Other (specify) Question: 1.1 Do you or a member of your household have access to training or advice for disease control measures, including one or more of the above-mentioned practices? Answer: Yes: 2 points No: 0 points | Question: 1.2 What has been the impact of diseases, especially fungal diseases like the black pod disease, on your yields the past two season? Answer: Very limited impacts (below 10%): 2 points Partially impacted (10% - 30%): 1 point Very impacted (more than 30%): 0 points |
| --- | --- |
| 2.1 Do you or a member of your household have access to cocoa village nurseries, seedling hybrids or services from germplasm stations? Answer: Yes: 2 points No: 0 points | 2.2 Is the cocoa planting material you use sufficient resistant to diseases and droughts, so you have stability in quality and quantity in your cocoa production even in years with high temperatures and/or limited rainfalls? Answer: Yes, they are resistant, increased (stable quality and quantity also under high temperatures and limited rainfall): 2 points Yes, they are resistant in most cases, 1 point No: 0 points |
| 3.1 Do you use organic fertilizers such as manure, or compost? Answer: Yes: 2 points No: 0 points | 3.2 During the past season, have you experienced increased production and increased gains (due to less expenses for industrial/chemical fertilizers)? Answer: Yes, production substantially increased, gains have increased: 2 points Yes, production slightly increased, gains not yet: 1 point No: 0 points |
| 4.1 How many of the following post-harvest activities do you employ? List of activities: - Standardized fermentation - Solar drying (adequate and protected drying) - Storage and warehousing - Increased access to market information and transport options Answer: Two or more activities: 2 points One activity: 1 point None: 0 points | 4.2 What have been your post-harvest losses during the past season? Answer: Less than 10% of total produce: 2 points Between 10%-30% of total produce: 1 point More than 30% of total produce: 0 points |
| 5.1 Do you or any member of your household participate in a group that have joint pre- or post- harvest activities with other farmers to improve your income from cocoa, like a Producer Organization (PO) (i.e. kuu group, cooperative, association, or other)? Answer: Yes: 2 points No: 0 points | 5.2 Have you observed any improvement in the income received from selling cocoa and/or processed products during the past season? Answer: Yes, substantially better price/better selling conditions: 2 points Yes, somewhat improved prices/selling conditions: 1 point No: 0 points |
| Additional Question (to be asked before Question 6.1): Have you or any member of your household attended trainings on any of the following practices? Answer: Yes or No (No points will be allocated for this answer) 6.1 Have you or any member of your household adopted any practices learned in the following trainings? List of Trainings: - Field Layout and Field Planning - Cocoa pre-plantation Activities - Crop Maintenance - Rehabilitation through under brushing, pruning and shade management - Flowering and pod production - Cocoa post-harvest activities - Market and market chain analysis - Record keeping - CC and climate adaptation - Procedure for Starting Agro-Ecosystem Analysis Answer: Yes, adopted practices from two trainings: 2 points Yes, adopted practices from 1 training: 1 point No: 0 points | 6.2 Are the trainings you have had on cocoa production and marketing equipping you to stabilize and increase your yields and business potential. Answer: Both yield AND business potential have improved the last season thanks to my skills and learning: 2 Either yield OR business potential has improved the last season thanks to my skills and learning: 1 No: 0 points |
| 7.1 Are your cocoa plantations complemented with a diverse selection of trees that provide shade and an optimal habitat for cocoa trees? Answer: Yes: 2 points No: 0 points | 7.2 Has the inclusion of shade trees helped diversify your income and/or increased cocoa productivity? Answer: Yes, other trees are producing alternate/new sources of incomes AND cocoa trees are more productive : 2 points Yes, shade trees provide alternative/new source of income OR help improve the productivity of cocoa trees: 1 point No: 0 Points |
| 8.1 Does your household harvest any crops other than cocoa? Answer: Yes, 2 or more crops: 2 points, Yes, 1-2 other crops: 1 point, No: 0 points | 8.2 Is income derived from crops other than cocoa substantial? Answer: Yes, more than 30%: 2 points Between 10% and 30%: 1 point Less than 10%: 0 points |
| 9.1 Have you in the past 2 years gained access to rehabilitated roads with drainage or improved road surface that protects against the risk of flooding? Answer: Yes: 2 points No: 0 points | 9.2 Is your farmland easily accessible during the rainy and dry seasons? Answer: Yes, in both season: 2 points Yes, only during one season: 1 point No: 0 points |

Reporting Requirements 
The consultant will be required to submit regular reports on the progress of the consultancy, including: 
a. Monthly progress reports: Monthly progress reports on the outcome survey, including any challenges or issues encountered. 
b. Final report: A final report on the consultancy, including the comprehensive value chain analysis report and recommendations for stakeholders. 
 2. Proposed Duration of Assignment 
 It is envisaged that the consultancy will take NINETY (90) days from the time the contract is signed. The Consultant/Consultancy Firm should develop a feasible cost-work plan/activity schedule covering a maximum of NINETY days and submit as integral part of the proposal for this consultancy. 
 3. PAYMENT SCHEDULE 
20% of the contract sum upon submission and acceptance of the first draft report against deliverable in the work schedule;
35% of the contract sum upon submission and acceptance of the second draft  report against outline progress amounting to 55% physical completion of the assignment; 
45% of the contract sum upon submission of the final report acceptable to the PIU/MOA and IFAD. 
4. OUTCOMES/OUTPUTS 
At the end of the assignment, the following outputs/outcomes are expected: 
     I. Carry out data analysis, report writing and submit draft outcome report and raw data set (both hard & softcopies) to MOA/IFAD PIU for review.        
    II. Submit final report outlining key finding as per the outcome and impact indicators of the TCEP-II project objectives developed and submitted.        
 5.    RESPONSIBILITIES OF THE CLIENT (TCEPII) 
TCEPII/PIU shall be responsible for the following: 
i.   The consultant shall be given access to previous reports especially from sister project on demand 
ii.  Facilitate meetings with stakeholders of beneficiaries if required 
6. RESPONSIBILITIES OF THE CONSULTANT 
i.    The consulting firms shall be responsible for the accommodation, transportation and other operational  expenses  for their staff in the course of carrying out the assignment; 
ii.   Bear the cost of production of reports and related documents; 
 7. PROPOSED DURATION OF ASSIGNMENT 
It is envisaged that the consultancy will take 12 weeks from the time the contract is signed. The Consultancy Firm should develop a feasible cost-work plan/activity schedule covering a maximum of 12 weeks and submit as integral part of the proposal for this consultancy. 
8. REPORT SUBMISSION 
 A total of Four (4) copies of the report are to be submitted to the Project Coordinator Office.

9. REPORTING 
The Consultant shall report to the Project Coordinator through out the assignment while the M&E Officer is the focal person.

ANNEX 2

Qualification and Evaluation Criteria (Technical Evaluation)

| Item | Criteria | Points |
| --- | --- | --- |
| A. | Firm's general experiences/expertise and qualification | 10 |
|  | Must be a legally registered organization whose core activities are in research, and must have existed for at least 5 years. Must have experience in conducting baseline, mid-term, and endline evaluation or other similar study in the agriculture sector or other related fields in Liberia or within the sub-region. | 10 |
|  | Must be a legally registered organization whose core activities are in research, and must have existed for at least 4 years. Must have experience in conducting baseline, mid-term, and endline evaluation or other similar study in the agriculture sector or other related fields in Liberia or within the sub-region. | 8 |
|  | Must be a legally registered organization whose core activities are in research, and must have existed for at least 3 years. Must have experience in conducting baseline, mid-term, and endline evaluation or other similar study in the agriculture sector or other related fields in Liberia or within the sub-region. | 6 |
|  | Must be a legally registered organization whose core activities are in research, and must have existed for at least 2 years. Must have experience in conducting baseline, mid-term, and endline evaluation or other similar study in the agriculture sector or other related fields in Liberia or within the sub-region. | 4 |
| B. | Specific experience | 15 |
|  | Must have proven track records of successfully completing at least 10 projects in the similar field. This should be accompanied by at least reference letters and at least three certificates of successful and satisfactory completion of task in a given time. Submit evidence of at least 10 most recent projects completed. Proven skills in conducting computerized quantitative analysis, poverty assessment, gender and youth sensitive evaluations, stakeholders profiling and engagement, etc. | 15 |
|  | Must have proven track records of successfully completing at least 8 projects in the similar field. This should be accompanied by at least reference letters and at least three certificates of successful and satisfactory completion of task in a given time. Submit evidence of at least 8 most recent projects completed. Proven skills in conducting computerized quantitative analysis, poverty assessment, gender and youth sensitive evaluations, stakeholders profiling and engagement, etc. | 12 |
|  | Must have proven track records of successfully completing at least 6 projects in the similar field. This should be accompanied by at least reference letters and at least three certificates of successful and satisfactory completion of task in a given time. Submit evidence of at least 6 most recent projects completed. Proven skills in conducting computerized quantitative analysis, poverty assessment, gender and youth sensitive evaluations, stakeholders profiling and engagement, etc. | 8 |
|  | Must have proven track records of successfully completing at least 4 projects in the similar field. This should be accompanied by at least reference letters and at least three certificates of successful and satisfactory completion of task in a given time. Submit evidence of at least 4 most recent projects completed. Proven skills in conducting computerized quantitative analysis, poverty assessment, gender and youth sensitive evaluations, stakeholders profiling and engagement, etc. | 5 |
|  | Methodology and required Software Skills/ Knowledge | 25 |
|  | A Clear and well-structured research methodology to successfully carry out the task, including data management plan. Strong knowledge in the following software programs: CAPI, Kobo Collect, Survey Solutions, SPSS, Stata, Power BI. | 25 |
|  | A Clear and well-structured research methodology to successfully carry out the task, including data management plan. Strong knowledge in 5 of the following software programs: CAPI, Kobo Collect, Survey Solutions, SPSS, Stata, Power BI. | 20 |
|  | A Clear and well-structured research methodology to successfully carry out the task, including data management plan. Strong knowledge in 4 of the following software programs: CAPI, Kobo Collect, Survey Solutions, SPSS, Stata, Power BI. | 15 |
|  | A Clear and well-structured research methodology to successfully carry out the task, including data management plan. Strong knowledge in 3 of the following software programs: CAPI, Kobo Collect, Survey Solutions, SPSS, Stata, Power BI. | 10 |
| C | Firm’s Financial / Account Information with Evidence of Tax Clearance (TCC) and Audited Accounts for 2022, 2023 & 2024 | 10 |
|  | Firm’s financial/account information with at least 3 years of the relevant audited accounts and TCC | 10 |
|  | Firm’s financial/account information with at least 2 years of the relevant audited accounts and TCC | 6 |
|  | Firm’s financial/account information with at least 1 year of the relevant audited accounts and TCC | 4 |
|  | Firm’s financial/account information with only audited account | 2 |
| D | The qualifications of the key staff proposed for the Assignment | 40 |
|  | Survey/Project Manager/Research Specialist – Team Lead with 10 years experience. | 12 |
|  | Survey/Project Manager/Research Specialist – Team Lead with 8 years experience. | 10 |
|  | Survey/Project Manager/Research Specialist – Team Lead with 6 years experience. | 8 |
|  | Survey/Project Manager/Research Specialist – Team Lead with 4 years experience. | 6 |
| D(2) | Data Manager/ Data Analyst | 10 |
|  | Data Manager/ Data Analyst- with 8+ years experience | 10 |
|  | Data Manager/ Data Analyst- with 6+ years experience | 8 |
|  | Data Manager/ Data Analyst with 4+ years experience | 6 |
|  | Data Manager/ Data Analyst – with 2+ years experience | 4 |
| D(3) | Agricultural Specialist/Agricultural Economist | 10 |
|  | Agricultural Specialist/Agricultural Economist with 8+ years’ experience | 10 |
|  | Agricultural Specialist/Agricultural Economist with 6+ years’ experience | 8 |
|  | Agricultural Specialist/Agricultural Economist with 4+ years’ experience | 6 |
|  | Agricultural Specialist/Agricultural Economist with 2+ years’ experience | 4 |
| D(4) | M&E Specialist/Knowledge Management and Communication | 8 |
|  | M&E Specialist/Knowledge Management and Communication- with 8+ years’ experience | 8 |
|  | M&E Specialist/Knowledge Management and Communication- with 6+ years’ experience | 6 |
|  | M&E Specialist/Knowledge Management and Communication- with 4+ years’ experience | 4 |
|  | M&E Specialist/Knowledge Management and Communication- with 2+ years’ experience | 4 |
|  | Total Points | 100 |
|  | Minimum points required to pass | 70 points |

This document refers to legally constituted consulting firms as “consultant”.

The policy is accessible at www.ifad.org/anticorruption_policy.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/40738506.

The policy is accessible at https://www.ifad.org/en/document-detail/asset/41942012.

The Cross-Debarment Agreement was entered into by the World Bank Group, the Inter-American Development Bank, the African Development Bank, the Asian Development Bank and the European Bank for Reconstruction and Development, additional information may be located at: http://crossdebarment.org/.

Household Income and Expenditure Survey, LISGIS 2016

Compatible tablet models are listed on this webpage. http://support.mysurvey.solutions/customer/en/portal/articles/2505822-what-tablets-should-i-buy-